Action Plan – April 2015 to August 2016

ESC Region ___14___ or Other Organization ________

Date of Action Plan submitted to UNT ______8/3/2015______

Members of Partnership (Please list all)

| Name (include yourself) | District/University/Workforce or P-16 Council | Title/Position | Email | Phone |
| --- | --- | --- | --- | --- |
| Vicki Hayhurst | Region 14 ESC | AVATAR Lead/CTE Specialist | vhayhurst@esc14.net | 325-675-8669 |
| Roy Bartels | Western Texas College | Chief of Technology Officer | rbartels@wtc.edu | 325-574-7629 |
| Jacob Tiemann | Roscoe Collegiate HS | Director of ECHS/STEM | jtiemann@roscoe.esc14.net | 325-766-3629 |
| Abbie Randolph | Abilene P16 Council | Executive Director | Abbie.randolph@cisco.edu | 325-794-4463 |
| Gail Gregg | Abilene ISD | Executive Director of CTE | Gail.gregg@abileneisd.org | 325-677-14444 |
| Mary Ross | West Central Texas Workforce Solutions | Executive Director | Mary.ross@workforcesystem.org | 325-795-4301 |
| Kami Pruet | Region 14 ESC | ESC Consultant | kpruet@esc14.net | 325-675-8620 |
| Paula Kinslow | Clyde ISD | Director of Curriculum & Special Program | pkinslow@clydeisd.org | 325-893-4222 |

Goals of partnership (These sample goals should be modified to focus on your specific areas of endorsement and vertical alignment.)

- Develop ISD, post-secondary, and workforce/ P-16  partnerships appropriate to local endorsement options

- Facilitate offering  and documentation of College Preparatory Courses (CPCs) of the partnership

- Deepen vertical alignment of the ELA (this may be Math and/or Science) offerings of ISD and post-secondary partners

Objectives supporting your goals

- Systematically inventory and review the endorsement programs offered by regional high schools from the perspectives of alignment with post-secondary courses and programs to which they may be feeders and of regional workforce needs.

- Evaluate collaboratively its English Language Arts and Mathematics College Preparatory Courses, student learning outcomes, instructional strategies, and student and instructor expectations for alignment between secondary and post-secondary education so that high school students are prepared to enroll and succeed in post-secondary education.

- Review collaboratively the vertical alignment of any CTE courses locally developed by high schools with post-secondary courses and program to which they may feed.

Plan of Work

| # of Related Objective(s) Above | Activity | Planned Evidence of Implementation | Planned Evidence of Impact |
| --- | --- | --- | --- |
| 1 | To recognize endorsement programs offered by regional high schools align to certifications and post-secondary courses. | AVATAR Committee meetings minutes Documentation of awareness for Program of Study for students and parents. | Students and Parents awareness of endorsement programs alignment for secondary and post-secondary courses. |
| 3 | Create vertical alignment teams to study vertical alignment of CTE courses between secondary and post-secondary education. | Vertical alignment team meeting minutes Documentation of vertical alignment of Welding Program and Child Development Program. | Welding and Child Development Programs include participation of secondary and post-secondary education. |
| 2 | To continue conversation of implementation of ELA and Mathematics Preparatory Courses | AVATAR Committee meetings minutes Documentation of secondary and post-secondary education MOU | Students have the opportunity to participate in ELA and Mathematics preparatory courses |

Timeline, Responsibility, Resources, and Evaluation

| Date | Activity | Who is Responsible | Resources Needed | Associated Evaluation |
| --- | --- | --- | --- | --- |
| 9/10/2015 | AVATAR Regional Meeting-Introductions of Committee and review objectives and goals of grant, create vertical alignment teams | Vicki Hayhurst Kami Pruet | Committee Contact Info Grant goals and objectives AVATAR PPt | Meeting evaluation |
| 12/3/2015 | AVATAR Regional Meeting-Inventory of endorsement programs offered in the region/ Discussion related to ELA/Math Preparatory Course | Vicki Hayhurst Kami Pruet Committee members | List of endorsement programs ELA/Math Preparatory Courses being offered as of 9/1/2015 | Meeting evaluation |
| 3/24/2016 | AVATAR Regional Meeting-Connecting endorsement programs to workforce needs | Vicki Hayhurst Kami Pruet Committee members | Workforce Regional Data | Meeting evaluations Student survey for knowledge of endorsement programs/workforce needs |
| 6/16/2016 | AVATAR Regional Meeting-Review of yearly goals. | Vicki Hayhurst Kami Pruet Committee members | Grant goals and objectives AVATAR resources | Meeting evaluations Conference dissemination of information for Early Childhood endorsement program alignment for certification and/or post-secondary courses. |