Mid-term Status Report – May 2015 to March 2016

ESC Region 3

Date of this report Aril 15, 2016

Due on or Before April 15, 2016

- Members of Partnership

- Please list all partnership team members (leaders in the organizations you are working with on alignment projects) by name, affiliation, title, email and phone number, or confirm that all are correctly listed on the AVATAR website by checking here.  ___

| Name | District/University | Title | Email | Phone |
| --- | --- | --- | --- | --- |
| Babbet Lowe | Victoria College | Dean of Academic Foundations & Student Success | babette.lowe@victoriacollege.edu | 361-582-2581 |
| Jill Fox | U of H Victoria | Sr. Director, Living & Learning | foxje@uhv.edu | 361-570-4848 |
| Robin Nealy | Wharton County Jr. College | Instructor of English Department Head | rnealy@wcjc.edu | 281) 239-1590 |
| Sherry Lui | Wharton County Jr. College | Math Instructor | slui@wcjc.edu | 281-239-1590 |
| Mike Rivet | Formosa Plastics | Manager | mikerivet@ftpc.fpcusa.com | 361-987-7000 |
| Dr. Patty Shaffer | ESC 3 | Exe. Dir | pshafer@esc3.net | 361-573-0731 ext 202 |
| Charlotte Baker | ESC 3 | Deputy Exe. Dir | cbaker@esc3.net | 361-573-0731 ext 204 |
| Nan Gainer | ESC 3 | C&I Director | ngainer@esc3.net | 361-573- 0731 ext 214 |
| Mary Lea Pfenninger | ESC 3 | Specialist | mpfenninger@esc3.net | 361-573-0731 ext 225 |
| Cheryl Shamburger | ESC 3 | Specialist | cshamburger@esc.net | 361-573-0731 ext 297 |
| Gayle Parenica | ESC 3 | Specialist | gparenica@esc3.net | 361-573-0731 Ext292 |
| Sharon Foltyn | ESC 3 | Curriculum Director | sfoltyn@ganadoisd.net | 361-771-2280 |
| Shelly Dominguez | ESC 3 | Curriculum Director | sdominguez@iisd1.org | 361-284-3226 ext 1183 |

- Please identify members of your active Vertical Alignment Teams (faculty and staff who are engaged in the actual alignment work) with name, affiliation, title, e-mail address, and phone number, or confirm that all are correctly listed on the AVATAR website by checking here. ____

ELAR  VAT

| Gayle Parenica | ESC 3 | gparenica@esc3.net | 361-573-0731 ext 292 |
| --- | --- | --- | --- |
| Cheryl Shamburger | ESC 3 | cshamburger@esc.net | 361-573-0731 ext 297 |
| Sarah Woodring | ESC 3 | swoodring@esc3.net | 361-573-0731 ext 294 |
| Terri Smith Chavira | ESC 3 | tsmithchavira@esc3.net | 361-573-0731 ext 290 |
| Deborah Butler | Victoria College | deborah.butler@victoriacollege.edu | 361-573-3291 Ext 3327 |
| Lisa Bullock | Industrial ISD | lbullock@iisd1.org | (361) 284-3226 |
| Kayla Peters | Ganado ISD | kpeters@ganadoisd.org | (361) 771-3430 |
| Larry Rodriguez | Victoria ISD - WEST | larry.rodriguez@visd.net | (361) 788-2830 |
| Dana Bramble | Wharton County Jr. College | danab@wcjc.edu | 1-800-561-9252 ext 1584 |
| Jill Fox | University of Houston | foxje@uhv.edu | 361-570-4848 |
| Babbet Lowe | Victoria College | babette.lowe@victoriacollege.edu | 361-582-2581 |

Math VAT

| Name | District/University | Title | Email |
| --- | --- | --- | --- |
| Gayle Parenica | ESC 3 | gparenica@esc3.net | 361-573-0731 ext 292 |
| Cheryl Shamburger | ESC 3 | cshamburger@esc.net | 361-573-0731 ext 297 |
| Pam Yosko | ESC 3 | pyosko@esc3.net | 361-573- 0731 ext 296 |
| Brian Hutcheson | Victoria College | brian.hutcheson@victoriacollege.edu | 361-582-2581 |
| Shana Zacek | Industrial ISD | szacek@iisd1.org | (361) 284-3226 |
| Elizabeth Teague | Ganado ISD | eteague@ganadoisd.org | (361) 771-3430 |
| Catherine Malloy | Victoria ISD- EAST | catherine.malloy@visd.net | (361) 788-2820 |
| Estella Villa | Liberty Academy, VISD | Estella.villa@visd.net | 361-788-9650 |
| Sherry Liu | Wharton County Jr. College | lius@wcjc.edu | 979-532-6395 |
| Jill Fox | University of Houston | foxje@uhv.edu | (361) 570-4848 |

- 2015-16 Goals of the Partnership.  Please note any modifications from the Action Plan or indicate “none.”

| # of Related Objective(s) Above | Status | Activity | Planned Evidence of Implementation | Planned Evidence of Impact |
| --- | --- | --- | --- | --- |
| 4 | Meeting Scheduled and document/ module in progress | Meet with CTE Focus group and present rough draft of alignment document | Sign in sheets/ Agenda | Module 3 will include some of this information instead of a handout. |
| 3 | First VAT module meeting 12/7/15 second scheduled 2/1/16 1st module in draft form 3rd VAT meeting Scheduled for 4/12/16 to work on Module 3 | VAT meetings in fall and (2) spring | Sign in sheet/ Agenda/ Modules | Module 1 complete, Module 2 in rough Draft Module 3 in progress |
| 2 | Working on modules and ppt Module 1 complete, Module 2 in rough Draft Module 3 in progress | Each of the modules will include benefits of taking CPC’s and will be part of Principal fall training with Leadership Component cooperation | PPT of benefits | PPT and training agenda from Principal training in fall |
| 1 | completed | Met with CTE Focus Group See attached summary | Sign in sheet/ Agenda | Alignment document to be created and distributed in R3 schools (This will not be done as described. Will include in module 3. Modules are taking up a significant amount of time.) |
| 2 | Completed | Bridges For Success Summit | Participation in Summit/ PPT and Sign in sheet | Summit evaluation |

- Status of Plan of Work

Please list the objectives associated with your 2015-16 goals in the table below and state the activities that have taken place since December 31, 2015, to further each objective.  State the results of each activity and any follow-up actions required to meet your objective.

- What are the major challenges or obstacles you have encountered since December, 2015, and what have you done to overcome them?

Time is always an obstacle.  Module 1 is finished.  Will upload to you ASAP.  Module 2 is almost complete and we just started on 3.  The content specialist are work AVATAR into their already busy schedule.  But things are coming along well.

- What are the dates of your major upcoming events if not stated in the table above?

All are stated.