Mid-term Status Report – May 2015 to December 2015

ESC Region 3

Date of this report 129/15

Due on or Before December 31, 2015

- Members of Partnership

Please list all partnership team members by name, affiliation, title, email and phone number.

| Patricia Schafer | 361-573-0731 ext 202 | ESC 3 | pshafer@esc3.net |
| --- | --- | --- | --- |
| Charlotte Baker | 361-573-0731 ext 204 | ESC 3 | cbaker@esc3.net |
| Nan Gainer | 361-573- 0731 ext 214 | ESC 3 | ngainer@esc3.net |
| Mary Lea Pfenninger | 361-573-0731 ext 225 | ESC 3 | mpfenninger@esc3.net |
| Cheryl Shamburger | 361-573-0731 ext 297 | ESC 3 | cshamburger@esc.net |
| Jill Fox | 361-570-4848 | University of Houston Victoria | foxje@uhv.edu |
| Babette Lowe | 361-582-2581 | Victoria College | babette.lowe@victoriacollege.edu |
| Mark Secord | 361-358-2838 | Coastal Bend College | secordmj@coastalbend.edu |
| Mike Rivet | 361-987-7000 | Formosa Plastics | mikerivet@ftpc.fpcusa.com |
| Shelly Dominquez | 361-284-3226 | Industrial ISD | sdominguez@iisd1.org |
| Sharon Foltyn | 361-771-3430 | Ganado ISD | sfoltyn@ganadoisd.net |
| Joann Gutierrez | 830-7802321 ext 300 | Karnes City ISD | jgutierrez@kcisd.net |
| G.G. Hunt | 1-800-561-9252 | Wharton County Jr. College | gghunt@wcjc.edu |
| Ashley Bergeron | 361-573-0731 Ext 237 | ESC 3 | abergeron@esc3.net |

Please identify members of your active Vertical Alignment Teams with name, affiliation, title, e-mail address, and phone number.

Name of VAT____ELAR________________________

| Gayle Parenica | ESC 3 | gparenica@esc3.net | 361-573-0731 ext 292 |
| --- | --- | --- | --- |
| Cheryl Shamburger | ESC 3 | cshamburger@esc.net | 361-573-0731 ext 297 |
| Sarah Woodring | ESC 3 | swoodring@esc3.net | 361-573-0731 ext 294 |
| Terri Smith Chavira | ESC 3 | tsmithchavira@esc3.net | 361-573-0731 ext 290 |
| Deborah Butler | Victoria College | deborah.butler@victoriacollege.edu | 361-573-3291 Ext 3327 |
| Mary Kay Best | Coastal Bend College | marykay@coastalbend.edu | (361) 354-2402 |
| Lisa Bullock | Industrial ISD | lbullock@iisd1.org | (361) 284-3226 |
| Kayla Peters | Ganado ISD | kpeters@ganadoisd.org | (361) 771-3430 |
| Stephanie Martinez | Karnes City ISD | smartinez@kcisd.net | (830) 780-2321 ext 300 |
| Larry Rodriquez | Victoria ISD - WEST | larry.rodriquez@visd.net | (361) 788-2830 |
| Dana Bramble | Wharton County Jr. College | danab@wcjc.edu | 1-800-561-9252 ext 1584 |
| Jill Fox | University of Houston | foxje@uhv.edu | 361-570-4848 |
| Ashley Bergeron | ESC 3 | abergeron@esc3.net | 361-573-0731 |

Name of VAT____Math________________________

| Name | District/University | Title | Email |
| --- | --- | --- | --- |
| Gayle Parenica | ESC 3 | gparenica@esc3.net | 361-573-0731 ext 292 |
| Cheryl Shamburger | ESC 3 | cshamburger@esc.net | 361-573-0731 ext 297 |
| Pam Yosko | ESC 3 | pyosko@esc3.net | 361-573- 0731 ext 296 |
| Ashley Bergeron | ESC 3 | abergeron@esc3.net | 361-573-0731 ext 237 |
| Brian Hutcheson | Victoria College | brian.hutcheson@victoriacollege.edu | 361-582-2581 |
| Mary Kay Best | Coastal Bend College | marykay@coastalbend.edu | 361-825-3025 |
| Cheryl Weixelman | Industrial ISD | cweixelman@iisd1.org | (361) 284-3226 |
| Elizabeth Teague | Ganado ISD | eteague@ganadoisd.org | (361) 771-3430 |
| Lorrie Lara | Karnes City ISD | llara@kcisd.net | (830) 780-2321 ext 300 |
| Catherine Malloy | Victoria ISD- EAST | catherine.malloy@visd.net | (361) 788-2820 |
| Kathy Rod | Wharton County Jr. College | kathyr@wcjc.edu | 1-800-561-9252 |
| Jill Fox | University of Houston | foxje@uhv.edu | (361) 570-4848 |

- 2015-16 Goals of the Partnership.  Please note any modifications from the Action Plan. Modification in Red

- Status of Plan of Work

Please list the objectives associated with your goals in the table below and state the activities that have taken place to further each objective.  State the results of each activity and any follow-up actions required to meet your objective.

See above

| # of Related Objective(s) Above | Status | Activity | Planned Evidence of Implementation | Planned Evidence of Impact |
| --- | --- | --- | --- | --- |
| 4 | Meeting Scheduled and document in progress | Meet with CTE Focus group and present rough draft of alignment document | Sign in sheets/ Agenda | List documenting college and HS endorse alignment |
| 3 | First VAT module meeting 12/7/15 second scheduled 2/1/16 1st module in draft form | VAT meetings in fall and spring | Sign in sheet/ Agenda/ Modules | Creation of 2 modules. See attached documentation |
| 2 | Working on modules and ppt | Each of the modules will include benefits of taking CPC’s and will be part of Principal fall training with Leadership Component cooperation | PPT of benefits | PPT and training agenda from Principal training in fall |
| 1 | Worked in cooperation with CTE Focus Group | Met with CTE Focus Group See attached summary | Sign in sheet/ Agenda | Alignment document to be created and distributed in R3 schools |
| 2 | Completed | Bridges For Success Summit | Participation in Summit/ PPT and Sign in sheet | Summit evaluation |

- What challenges or obstacles have you encountered and what have you done to overcome them?

We have had difficulty with getting responses from WCJC and CBC.  They have not responded to our emails or phone calls.  With the change of leadership at CBC, I knew there might be some difficulty, but with talking to Mr. Secord at great length, I thought everything was fine.  I will be calling and sending copies of the work we did at our first module meeting in hope they see the work and want to be part of it.

- What assistance would be helpful to you?  Another phone call to WCJC and CBC would be helpful.  I have emailed CBC and they are reconsidering their participation in the project.  They are under a new Academic Head.  I emailed Wharton and they finally responded.  They are looking into participating more actively.