Action Plan – January to August 2016

Texarkana College

Date of Action Plan submitted to UNT  - 1/29/16

Members of Partnership (Please list all)

| Name (include yourself) | District/University/Workforce or P-16 Council | Title/Position | Email | Phone |
| --- | --- | --- | --- | --- |
| Melisa Jones | Texarkana College | Coordinator for Developmental Education | Lisa.jones@texarkanacollege.edu | 903 823 3223 |
| Dr. Tonya Hill | Texas A&M Texarkana | Director of TRIO Student Support Services | Tonya.hill@tamut.edu | 903 334 6656 |
| Sandra Shingleur | Workforce Solutions of Northeast Texas | Workforce and Education Training Project Manager | Sandra.shingleur@netxworks.org | 903 794 9490 |
| Pam Montgomery | DeKalb ISD | Math Instructor | Pam.montgomery@dekalbisd.net | 903 667 2422 |
| Lori Shelton | DeKalb ISD | English Instructor | Lori.shelton@dekalbisd.net | 903 667 2422 |
| Lea Dooley | DeKalb ISD | Counselor | Lea.dooley@dekalbisd.net | 903 667 2566 |
| Neilan Hensley | DeKalb ISD | Principal | Neilan.hensley@dekalbisd.net | 903 667 2422 |

Goals of partnership (These sample goals should be modified to focus on your specific areas of endorsement and vertical alignment.)

- Develop ISD, post-secondary, and workforce/ P-16  partnerships appropriate to local endorsement options

- Facilitate offering  and documentation of College Preparatory Courses (CPCs) of the partnership

- Deepen vertical alignment of the ELA and Math offerings of local ISDs and post-secondary partners

Objectives supporting your goals

1. Increase knowledge and understanding of College Preparatory Courses among local ISDs through the ISD, post-secondary, and workforce partnerships

2. Develop a common documentation system for notation of College Preparatory Course completion on high school transcripts and reporting system for course data

3. Develop vertical alignment documents, teacher resources, and a share point for College Preparatory ELA and Math partners

Plan of Work

| # of Related Objective(s) Above | Activity | Planned Evidence of Implementation | Planned Evidence of Impact |
| --- | --- | --- | --- |
|  | Professional development for local ISDs focusing on College Preparatory Courses | Professional development attendance; Article and photographs highlighting event | Survey participants immediately following event and again once the new semester begins |
|  | Partnership meeting to develop reporting documents | Meeting agenda Final documents – transcript format, spreadsheet for data | Ease of end of semester data reporting and student registration |
|  | Partnership meeting to share needs, resources, and alignment elements | Meeting agenda Resource share point Final documents/site | Growth of offerings in College Preparatory Courses at ISDs, Sharing of resources, Increase in communication among partners |

Timeline, Responsibility, Resources, and Evaluation

| Date | Activity | Who is Responsible | Resources Needed | Associated Evaluation |
| --- | --- | --- | --- | --- |
| Jan. 30 | Submit Plan | Melisa Jones |  |  |
| Feb. 2 | Conference Call | Melisa Jones |  |  |
| On or before March 4 | Partnership Meeting (Goals, Objectives, Resources, Alignment) | Partners | College DE Instructors | Minutes of the meeting will illustrate that goals and objectives were met for the meeting |
| April | Regional Meeting | Melisa Jones |  |  |
| On or before April 1 | Partnership Meeting (Documents, Other Region Ideas) | Partners | Presenter | Minutes of the meeting will illustrate that goals and objectives were met for the meeting |
| On or before June 3 | Professional Development | Partners |  | Seventy-five percent of participants surveyed will indicate that the sessions provided resources and information that will help make students successful in the College Preparatory Courses |
| June 7 | Conference Call | Melisa Jones |  |  |
| Aug. 15 | Final Report Action Plan 2016-17 | Melisa Jones |  |  |

Budget plan

| Anticipated activity | Personnel cost/Stipends | Travel | Materials/Supplies | Food | Consultant |
| --- | --- | --- | --- | --- | --- |
| March Partnership Meeting | $50 Sub pay for ISD teachers (2) = $100 $50 DE Instructor Stipends (4) = $200 |  |  | 12 boxed lunches = $200 |  |
| April Partnership Meeting | $50 Sub pay for ISD teachers (2) = $100 | Presenter – hotel, mileage, and food $300 |  | Breakfast food for 10 = $100 |  |
| June Professional Development | $200 Stipends for ISD presenters (3)= $600 |  | Copies/Handouts/Resources for ISD instructors (30-40) = $600 | Breakfast food for 50 = $300 |  |
| TOTAL | $1000 | $300 | $600 | $600 |  |