Region 1: UTPA, STC, PSJA

Action & Sustainability Plan

2012-2013 Target Content: Chemistry

| Action | What | When | Where | How | Who | Outcome |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Participate in VAT training |  |  |  |  |  |
|  | Attend AVATAR Partner Training | 8/13/12 | Fort Worth | Participation in training | Laura Saenz-UTPA Cindy Valdez-UTPA Wally Johnson-STC Tina McIntyre-Reg I David Garza-PSJA Luis Suarez-PSJA | Introductory knowledge acquired |
|  | AVATAR Video Conference | 8/28/12 | Region One |  | Laura Saenz-UTPA Cindy Valdez-UTPA Barbara Gonzalez-Reg I Daniel Plas-UTPA | Clarification of timeline and expectations for AVATAR |
| 2. | Form and sustain partnerships |  |  |  |  |  |
|  | Partner meeting | 10/26/12 | UTPA | Face-to-face meeting | Laura Saenz-UTPA Cindy Valdez-UTPA Daniel Plas-UTPA David Garza-PSJA Wally Johnson-STC Ludy Avila-STC | Initial meeting held |
|  | Partner meeting | 11/9/12 | UTPA | Face-to-face meeting | Laura Saenz-UTPA Daniel Plas-UTPA David Garza-PSJA Israel Nicanor-PSJA Ludy Avila-STC Mahmoud Gassem-STC | Additional key partners identified and attended |
|  | Partner meeting | 11/30/12 | UTPA | Face-to-face meeting | Laura Saenz-UTPA Daniel Plas-UTPA Tim Sears-UTPA John Villarreal-UTPA David Garza-PSJA Luis Suarez-PSJA Israel Nicanor-PSJA Ludy Avila-STC Mahmoud Gassem-STC | Additional key partners identified and attended |
| 3. | Collect and report regional data to use in aligning decision making and follow up |  |  |  |  |  |
|  | Collect and report initial data from publicly available sites | 9/24/12 |  |  | Laura Saenz-UTPA | Powerpoint developed and submitted to AVATAR |
|  | Submit and certify PSJA data to THECB | 1/31/13 | PSJA |  | PSJA, UTPA & STC Laura Saenz-UTPA | Pathways reports provided by THECB |
| 4. | Create shared understandings | 1/9/13 | UTPA | Face-to-face meeting | Laura Saenz-UTPA Daniel Plas-UTPA Tim Sears-UTPA John Villarreal-UTPA Chris Smith- UTPA David Garza-PSJA Luis Suarez-PSJA Israel Nicanor-PSJA Ludy Avila-STC Mahmoud Gassem-STC | Developed shared understanding of alignment Identified key goals Identified data requests |
| 5. | Determine goals |  |  |  |  |  |
|  | Short-term goals | Started: 1/9/13 and ongoing |  |  | All team members | -Develop exit/entry level assessments for chemistry courses at the secondary level -Examine the predictive power of Algebra II performance to post-secondary Chemistry performance -Develop self-assessments for teachers to become basis for professional development to be provided |
|  | Long-term goals | Started: 1/9/13 and ongoing |  |  | All team members | Provide professional development to teachers |